## Cover
AACS Work Schedule
Document Information
Issuing authority | Team 3
Version | Date | Comment | Author
1 | 2021-06-17 | Initial Version | Team 3

## WBS
Phase | Part | Level 1 | Level 2 | Owner | Week 1 | [9 empty] | Week 2 | [9 empty] | Week 3 | [9 empty] | Week 4 | [9 empty] | Week 5
[5 empty] | 1-A | 1-P | 2-A | 2-P | 3-A | 3-P | 4-A | 4-P | 5-A | 5-P | 1-A | 1-P | 2-A | 2-P | 3-A | 3-P | 4-A | 4-P | 5-A | 5-P | 1-A | 1-P | 2-A | 2-P | 3-A | 3-P | 4-A | 4-P | 5-A | 5-P | 1-A | 1-P | 2-A | 2-P | 3-A | 3-P | 4-A | 4-P | 5-A | 5-P | 1-A | 1-P | 2-A | 2-P | 3-A | 3-P | 4-A | 4-P | 5-A | 5-P
Phase 1 | Process | Team Building |  | All | P | P
[5 empty] | W | W
|  | Project Plan |  | Gyeonghun Ro | P | P
[5 empty] | W | W
|  | Requirement Analysis |  | All | [7 empty] | P | P | P | P
[12 empty] | W | W | W
|  | Project Analysis |  | All |  |  | P | P |  | P | P | P
[7 empty] | W | W |  | W | W
|  | Risk management |  | All |  |  |  |  | P | P
W
|  | Software Design | Data Flow Diagram | All | [10 empty] | P | P | P | P
[15 empty] | W | W | W
|  | Threat Modeling |  | All | [13 empty] | P | P | P
[18 empty] | W | W | W | W
|  | Architecuture Design |  | Gyeonghun Ro | [15 empty] | P | P | P | P | P | P | P | P | P
[20 empty] | W | W | W | W | W | W
|  | Vulnerability Analysis |  | Vibhanshu Hyejin Oh | [15 empty] | P | P | P | P | P | P | P | P | P
[20 empty] | W | W | W | W | W | W
|  | Key management |  | Kyuwoon Kim Hyejin Oh | [23 empty] | P | P | P | P
[28 empty] | W | W | W
|  | Documentation |  | Gyeonghun Ro Hyejin Oh | [23 empty] | P | P | P | P | P
[29 empty] | W | W | W | W
| Attendance Check System(ACS) | Communication Manager |  | Hyungjin Choi | [17 empty] | P | P | P | P | P | P | P | P | P | P | P
[22 empty] | W | W | W | W | W | W | W | W | W | W
|  | User Auth Manager |  | Kyuwoon Kim | [17 empty] | P | P | P | P | P | P | P | P | P | P | P
[22 empty] | W | W | W | W | W | W | W | W | W | W
|  | Config setting |  | Wonyoung Chang | [17 empty] | P | P | P | P | P | P | P | P | P | P | P
[22 empty] | W | W | W | W | W | W | W | W | W | W
|  | Student Controller |  | Wonyoung Chang | [20 empty] | P | P | P | P | P | P | P | P
[25 empty] | W | W | W | W | W | W | W
|  | Attendance Controller |  | Wonyoung Chang | [20 empty] | P | P | P | P | P | P | P | P
[25 empty] | W | W | W | W | W | W | W
| Face Recognition System(FRS) | Communication Manager |  | Hyungjin Choi | [17 empty] | P | P | P | P | P | P | P | P | P | P | P
[22 empty] | W | W | W | W | W | W | W | W | W | W
|  | User Auth Manager |  | Soohyun Yi | [17 empty] | P | P | P | P | P | P | P | P | P | P | P
[22 empty] | W | W | W | W | W | W | W | W | W | W
|  | Encryption/Hash |  | Kyuwoon Kim | [17 empty] | P | P | P | P | P | P | P | P | P | P | P
[22 empty] | W | W | W | W | W | W | W | W | W | W
|  | Signing/Verify |  | Kyuwoon Kim | [17 empty] | P | P | P | P | P | P | P | P | P | P | P
[22 empty] | W | W | W | W | W | W | W | W | W | W
|  | Face Manager |  | Soohyun Yi | [21 empty] | P | P | P | P | P | P | P
[26 empty] | W | W | W | W | W | W
|  | AI Manager |  | Hyungjin Choi | [21 empty] | P | P | P | P | P | P | P
[26 empty] | W | W | W | W | W | W
Phase 2 | Architecture Analysis | Context Diagram |  | Gyeonghun Ro | [30 empty] | P | P | P
[35 empty] | W | W
|  | Dynamic View |  | Gyeonghun Ro | [31 empty] | P | P | P
[36 empty] | W | W
|  | TCSEC / ITSEC |  | Gyeonghun Ro | [29 empty] | P | P
[34 empty] | W | W
|  | Common Criteria |  | Gyeonghun Ro | [30 empty] | P | P
[35 empty] | W | W
| Common Creitria | EAL1 Analysis |  | Gyeonghun Ro | [32 empty] | P | P | P | P
[37 empty] | W | W | W
|  | EAL1 Assessment |  | Gyeonghun Ro | [43 empty] | P | P | P | P | P | P
[48 empty] | W | W | W | W | W
| Vulnerability Analysis | UserRegister |  | Soohyun Yi | [42 empty] | P | P | P | P
[47 empty] | W | W | W
|  | CCTV |  | Soohyun Yi Vibhanshu | [43 empty] | P | P | P | P
[48 empty] | W | W | W | W
|  |  |  | Wonyoung Chang | [34 empty] | P | P | P | P
[39 empty] | W | W | W | W
|  | MonitoringSystem |  | Kyuwoon Kim Hyungjin Choi Wonyoung Chang | [44 empty] | P | P | P
[49 empty] | W | W | W
|  | Camera |  | Kyuwoon Kim Gyeonghun Ro | [36 empty] | P | P
[41 empty] | W | W
|  | Communicaiton |  | Kyuwoon Kim Hyungjin Choi | [35 empty] | P | P | P | P | P
[40 empty] | W | W | W | W | W
|  | Static Analysis (Rats, SonarCloud) |  | Soohyun Yi Hyungjin Choi | [31 empty] | P | P
[36 empty] | W | W
|  | Open Source Vulnerability |  | Wonyoung Chang | [32 empty] | P | P | P
[37 empty] | W | W | W
|  | Vulnerability Scanner (NESSUS, nmap) |  | Hyejin Oh Wonyoung Chang | [32 empty] | P | P | P | P
[37 empty] | W | W | W | W
| Attack Vector Analysis | User Register |  | Soohyun Yi | [37 empty] | P | P
[42 empty] | W | W
|  | Camera |  | Gyeonghun Ro | [38 empty] | P
W
|  | Communication |  | Kyuwoon Kim Hyungjin Choi | [36 empty] | P | P | P | P
[41 empty] | W | W | W | W
| Report | Final Presentation |  | ALL | [44 empty] | P | P | P | P | P | P
[49 empty] | W | W | W | W | W | W